## Sheet1
Description | Evaluation | Likelihood | Impact | Responsibility | Response | Control Measures | Risk Level
Devlopers being absent / sick | Can results in delays for the project | Medium | Low | Developer | Find cover and proritise MVP. |  | Medium
Ineptitude | Results in delays, time spent to upskill. | Low | Medium | Developer | Upskill, or ask for help from trainer. | Stay up to date with learning. | Low Medium
Remote Attack on database | Customer data could be stolen or manipulated. | Medium | High | Developer | Contact Customers, ensure strong credentials | Use password hashing. | Medium High
Confidential credentials being shared. | Allows person to access VCS and Database. | Low | High | Developer |  | Have encrypted files which hold sesitive information | Medium
SQL Injection | Hacker can manipulate database. | Low | High | Developer | Change credentials, find changes made to database. | Make sure there are no vulnerabilities in code. | Medium
Database deletion | Data will be temporariliy lost | Low | Low | Developer | Restore data from back ups. | Regular back ups. | Low
Computer damaged | Delays in project, potential loss of work. | Low | Medium | Developer | Restore data from back ups. |  | Low Medium
GitHub goes down. | Delays in project, potential loss of work. | Low | High | GitHub |  | Keep Local copy of files. | Medium
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High